## FP3
REVIEW OF MILESTONES 2020: COVID-19 IMPACT RISK ASSESSMENT
1.Research/ science - inherent risk in unknown cutting-edge research or science | 2. Financial - funding not fully confirmed or at risk of being cut | 3. Partnership- risk that partners won’t be able to deliver a key piece on time | 4. Internal resources- risk that key staff, infrastructure or equipment not available at time needed | 5. Weather - for example, drought or heavy rain affecting field trials | 6. External environment (political, economic, legal, market) - e.g. risk of non- delivery due to conflict, economic/ market changes | 7. Others. Please specify in the next column
Yes | No
Low | Medium | High
Yes (Please update the deliverable/s in MEL) | No
Flagship Program 3: Integrated Farm and Household Management
To be filled by FP Leaders
| No. | FP | Mapped to Sub-IDO | 2022 FP outcomes | Milestone | Source | Means of verification | CGIAR Cross-Cutting Markers for the milestone |  |  |  | Assessment of risk to achieve milestone: Low/Medium/High | For medium/ high please specify the main risk | Will adjustments be made in due to COVID-19 impact? (Yes/No) | Limitations/ Challenges | Opportunities | Adjustments to be made (if any) | Assessment of risk to achieve adjustments on milestones: Low/Medium/High (Select from the list) | For medium/high please select the main risk from the list | For risk, if you choose the option of 'Others', please specify. | Do you anticipante any change in the planned deliverable/s (Yes/No)
[8 empty] | for gender | for youth | for CapDev | for CC
| 1 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O1. Cropping systems sustainably intensified and diversified | 5,000 farmers in project sites increase the diversity within cropping systems and use water and soil management practices developed jointly by farmers and researchers | Reworded/ rephrased from proposal | Research and evaluation reports, training manuals, fact sheets and other extension materials | 1 | 0 | NA | 1 | Medium | 2. Financial - funding not fully confirmed or at risk of being cut | Yes | 1) Farmer training sessions and field days in countries where the cropping season had already started were cancelled or postponed due to restrictions on travel and gatherings; and also limited farmer training sessions in countries where the cropping season began later; 2) Delayed acquisition of inputs such as seeds, fertilizer and crop protection products; 3) Limited establishment and monitoring of on-farms trials | 1) Travel restrictions and lockdown measures decreased imports and increased internal demands for local technologies and products in some countries. For example, in Mozambique farmgate prices for soybean and most of the other grain legumes were higher than typical around the same period in previous seasons; in Nigeria demands for cowpea and soybean seeds were higher than previous years; 2) opportunity to train farmers to increase productivity to meet local demand | 1) Some training sessions were rescheduled and also limited training sessions and field days to 10 people at a time, provided PPEs such as masks, groves, hand sanitizers and hand washing facilities; 2) Some partnership meetings were done virtually; 3) Relied exclusively in some cases on local staff or partners and lead farmers to conduct monitoring and field training where possible | Low |  |  | No
| 2 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O1. Cropping systems sustainably intensified and diversified | Agricultural system simulation models (agent-based model, nutrient balance/ flow models) used to assess ex-ante impacts of innovation practices on crop production efficiency and household livelihoods, and best- bet options identified | New | Operational models; reports on ex post impact assessment with an efficiency focus; publications (submitted journal article, conference proceeding paper) | NA | NA | NA | NA | Medium | 2. Financial - funding not fully confirmed or at risk of being cut | Yes | 1) Delayed acquisition of inputs such as seeds, fertilizer and crop protection products; 2) Limited establishment and monitoring of on-farms trials; 3) Delayeed data collection |  | 1) Organized online meetings with partners; 2) Relied on project partners for some data collection | Low |  |  | No
| 3 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O1. Cropping systems sustainably intensified and diversified | Participatory field trials under smallholder conditions in different cropping systems under different environments evaluated | New | Reports on field trials and publications | 1 | 0 | NA | 1 | Medium | 5. Weather - for example, drought or heavy rain affecting field trials | Yes | 1) Farmer training sessions and field days in countries where the cropping season had already started were cancelled or postponed due to restrictions on travel and gatherings; and also limited farmer training sessions in countries where the cropping season began later; 2) Delayed acquisition of inputs such as seeds, fertilizer and crop protection products; 3) Limited establishment and monitoring of on-farms trials | 1) Travel restrictions and lockdown measures decreased imports and increased internal demands for local technologies and products in some countries. For example, in Mozambique farmgate prices for soybean and most of the other grain legumes were higher than typical around the same period in previous seasons; in Nigeria demands for cowpea and soybean seeds were higher than previous years; 2) opportunity to train farmers to increase productivity to meet local demand | 1) Some training sessions were rescheduled and also limited training sessions and field days to 10 people at a time, provided PPEs such as masks, groves, hand sanitizers and hand washing facilities; 2) Some partnership meetings were done virtually; 3) Relied exclusively in some cases on local staff or partners and lead farmers to conduct monitoring and field training where possible | Low |  |  | No
| 4 | 3 | Reduced production risk | FP3.O2. Pest and diseases controlled safely and with reduced agro-chemical inputs | Pest and diseases management components for the target; and resource and soil management options in different regions fine-tuned | Same as 2019 (to be removed, and merged with milestone below as discussed with Jules and Manu: Effective pest and disease management components evaluated for controlling target pests; and resource and soil management options evaluated for improved resilience) | Reports | 1 | 1 | 1 | 1 | Medium | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | [8 empty] | confirmed by Manu
| 5 | 3 | Reduced production risk | FP3.O2. Pest and diseases controlled safely and with reduced agro-chemical inputs | Efficacy of selected pest and diseases management; and resource and soil management options confirmed at pilot scale | Same as 2019 (to be removed, and merged with milestone below as discussed with Jules and Manu: Effective pest and disease management components evaluated for controlling target pests; and resource and soil management options evaluated for improved resilience) | Publication and reports | 1 | 1 | 1 | 1 | Medium | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | [8 empty] | confirmed by Manu
| 6 | 3 | Reduced production risk | FP3.O2. Pest and diseases controlled safely and with reduced agro-chemical inputs | Effective pest and disease management components evaluated for controlling target pests; and resource and soil management options evaluated for improved resilience | Reworded/ rephrased from proposal: note this is the merger of the two above milestones as discussed with Jake, so it replaces them | Publication and reports | 1 | 1 | 1 | 1 | Medium | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | Yes | 1) releases of biocontrol agents against the pod borer might be delayed due to cross-border travel restricitions; 2) Collection of new isolates of DM and blast pathogens of pearl millet from farmers’ fields in 2019 might be hampered due to travel restrictions; 3)Dealy in conducting some experiments related to biopesticides; 4) Field evaluation of non-toxigenic Aspergillus flavus strains may get affected if the COVID-19 situation extends until October, 2020; 5) Partial lockdown affected the preapration of trials and backstopp training of partenrs in Burkina Faso and Mali not possible because of border closure; 6) delay in acquiring data of viral sequencing and in acquiring data of yield impact in the fields |  | 1) total numbers of parasitoids released and/or release areas may be less than anticipated; 2) none; 3) none; 4) In case field experiment is not possible, only glasshouse experiment data can be generated; 5) Testing of FAW and millet head miner egg parasitoids will be limited to Niger only; 6) experiments will be made in greenhouses | Low |  |  | No | confirmed by Manu
| 7 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O3. Tested, adapted and validated options applied for sustainable intensification and livelihood diversification by farmers | Suite of systems modelling tools/ framework for co- designing resilient farming systems in GLDC regions | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | https://www. mdpi.com/2077- 0472/9/9/185/htm | 1 | NA | NA | NA | High | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | [8 empty] | confirmed by Jules and Shalander
| 8 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O3. Tested, adapted and validated options applied for sustainable intensification and livelihood diversification by farmers | Household modelling and sustainabilty assessment tools as decision-support for enhanced farming system resilience validated and piloted | New 2020 POWB (post midyear review)- to continue the work done in the completed milestone "Suite of systems modelling tools/ framework for co- designing resilient farming systems in GLDC regions". | Field data, workshop reports | 1 | NA | 1 | 2 | High | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | Yes | The field level piloting of systems modelling tools is being affected due to COVID19 | We have established good network of NARS and extnsion system actor to validate and pilot the tools. | We continue to work on systems modeeling tools,but piloting of tools will be done in 2021. | Low |  |  | Yes (Please update the deliverable/s in MEL)
| 9 | 3 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP3.O3. Tested, adapted and validated options applied for sustainable intensification and livelihood diversification by farmers | Portfolios of household activities, enterprises and management practices that materially and equitably enhance livelihoods (as defined at sub-IDO level) while minimizing negative externalities | Identical to proposal | https://cgspace. cgiar.org/ handle/10568/105731 | 1 | NA | NA | NA | High | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | Yes | NARES partners and our teams could only partially implement the identified portfolios. Some of the stakeholder sdiverted funding to deal with COVID19. | We have come up with covid response strategies which arebeing utilized by stakeholders and policy makers. | We have established good network with multiple NARES institutions and would continue to work with them next year as well. | Low |  |  | Yes (Please update the deliverable/s in MEL)