## FP1
REVIEW OF MILESTONES 2020: COVID-19 IMPACT RISK ASSESSMENT
1.Research/ science - inherent risk in unknown cutting-edge research or science | 2. Financial - funding not fully confirmed or at risk of being cut | 3. Partnership- risk that partners won’t be able to deliver a key piece on time |  | 4. Internal resources- risk that key staff, infrastructure or equipment not available at time needed | 5. Weather - for example, drought or heavy rain affecting field trials | 6. External environment (political, economic, legal, market) - e.g. risk of non- delivery due to conflict, economic/ market changes | 7. Others. Please specify in the next column
Yes | No
Low | Medium | High
Yes (Please update the deliverable/s in MEL) | No
Flagship Program 1: Priority Setting and Impact Acceleration
To be filled by FP1 Leader
| No. | FP | CoA | Mapped to Sub-IDO | 2022 FP outcomes | Milestone | Source | Means of verification | CGIAR Cross-Cutting Markers for the milestone |  |  |  | Assessment of risk to achieve milestone: Low/Medium/High | For medium/ high please specify the main risk | Will adjustments be made in due to COVID-19 impact? (Yes/No) | Limitations/ Challenges | Opportunities | Adjustments to be made (if any) | Assessment of risk to achieve adjustments on milestones: Low/Medium/High (Select from the list) | For medium/high please select the main risk from the list | For risk, if you choose the option of 'Others', please specify. | Do you anticipante any change in the planned deliverable/s (Yes/No) | Comments
[9 empty] | for gender | for youth | for CapDev | for CC
| 1 | 1 | 1.1 | Increased resilience of agro- ecosystems and communities, especially those including smallholders | FP1.01. Improved targeting and responsiveness of research to market and household demands in the face of climate change for greater technology adoption, food and nutrition security, resilience, and poverty reduction | Ex-ante evaluation of GLDC research and technology options completed and working papers published on the potential poverty and nutrition security impacts to guide priority setting | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Foresight and ex-ante evaluation working papers and the final results that will be shared with GLDC researchers and stakeholders at the annual review and planning meeting | 0 | 0 | 0 | 1 | Low | [9 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 2 | 1 | 1.1 | Increased availability of diverse nutrient-rich foods | FP1.01. Improved targeting and responsiveness of research to market and household demands in the face of climate change for greater technology adoption, food and nutrition security, resilience, and poverty reduction | Multidimensional ex-ante evaluation of GLDC research and technology options completed and results shared with GLDC staff and partners | Reworded/ rephrased from proposal | Refined GLDC program with adjusted work plans for 2021 featuring priority research options and countries | NA | NA | NA | NA | Medium | 4. Internal resources - risk that key staff, infrastructure or equipment not available at time needed | No | [6 empty] | No
| 3 | 1 | 1.2 | Increased livelihood opportunities | FP1.02. Market and household demand identified, and trade- offs assessed for more inclusive value chains that improve income and nutrition status in target regions | Diversity of farm household preferences vis-a-vis market demand by context outlined in view of research in GLDC | Reworded/ rephrased from proposal (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Types of market demands and value chain-based interventions identified | NA | NA | NA | NA | Medium | 4. Internal resources - risk that key staff, infrastructure or equipment not available at time needed | [8 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 0 | 1 | 1.2 | Increased livelihood opportunities | FP1.02. Market and household demand identified, and trade- offs assessed for more inclusive value chains that improve income and nutrition status in target regions | Shared learning across GLDC stakeholders and FPs on implications of diverse targets’ aspirations and future scenarios leading to strategic adjustments | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Report on diversity of target group preferences and match and mismatch of GLDC research targets based on meetings and workshops across GLDC | 1 | 1 | 1 | 0 | Low | [9 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 5 | 1 | 1.2 | Increased livelihood opportunities | FP1.02. Market and household demand identified, and trade- offs assessed for more inclusive value chains that improve income and nutrition status in target regions | Underlying principles established for diversity assessment and matching of technologies across contexts | Identical to proposal | Published options of how to meet the needs of diverse target groups in GLDC research and scaling | NA | NA | NA | NA | Medium | 4. Internal resources - risk hat key staff, infrastructure or equipment not available at time needed | No | [6 empty] | No
| 6 | 1 | 1.3 | Improved capacity of women and young people to participate in decision-making | FP1.03. Inclusive and equitable technologies and innovation systems established for accelerated and broadened impact across the agri-food system | Inclusive and equitable innovation system for accelerating impacts for women and young people designed and piloted including policy interactions. | Same as 2019 (This milestone has been changed in AR 2019. Old form: Inclusive and equitable innovation systems to accelerate impacts on women and young people designed and piloted underlying design principles proven.) | Reports on innovation systems for empowering women and youth; sex disaggregated and gender relevant datasets; policy brief [paper] on gender and social analysis informing intervention design | NA | NA | NA | NA | Medium | 6. External environment (political, economic, legal, market) - e.g. risk of non- delivery due to conflict, economic/ market changes | No | [6 empty] | No
| 7 | 1 | 1.3 | Improved capacity of women and young people to participate in decision- making | FP1.03. Inclusive and equitable technologies and innovation systems established for accelerated and broadened impact across the agri-food system | Inclusive and equitable innovation systems tested and adjusted to different biophysical and socioeconomic contexts, including policy interactions | Same as 2019 (This milestone has been cancelled in AR 2019, hence, to be dropped in POWB 2020) | Reports on the performance of innovation systems for women and youth in different contexts, including recommendations for enabling environments; synthesis report [paper] on improved capacities and skills for women and youth | 2 | 1 | 1 | 0 | Medium | 6. External environment (political, economic, legal, market) - e.g. risk of non- delivery due to conflict, economic/ market changes | [8 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 8 | 1 | 1.3 | Improved capacity of women and young people to participate in decision- making | FP1.03. Inclusive and equitable technologies and innovation systems established for accelerated and broadened impact across the agri-food system | Functioning innovation systems established across GLDC sites operating and sustainably; designing of scaling systems in collaboration with CoA 1.4 | Discontinued | Scaling out strategy for innovation systems for women and youth documented; number of women and youth impacted by interventions documented | NA | NA | NA | NA | Medium | 6. External environment (political, economic, legal, market) - e.g. risk of non-delivery due to conflict, economic/ market changes | [8 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 9 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | Joint systematic review with CoA 1.2 | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Review protocol | NA | NA | NA | NA | Low | [9 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 10 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | Scaling toolkit for Design, Execution, Monitoring, and Evaluation (DEME) content agreed upon to support improved horizontal and vertical scaling of GLDC commodities and management practices | Same as 2019 | Scaling toolkit framework | NA | NA | NA | NA | Medium | 4. Internal Resources - risk that key staff, infrastructure or equipment not available at time needed | No | [6 empty] | No
| 11 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | Evaluation designed and implementation underway to evaluate current GLDC scaling approaches and associated impact evidence | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Evaluation design reports | NA | NA | NA | NA | Low | [9 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 12 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | Evaluation documenting the strengths, shortcomings, and key lessons learnt on GLDC scaling approaches and impacts | Same as 2019 | Evaluation report | 1 | 1 | 1 | 1 | Medium | 3. Partnership - risk that partners won’t be able to deliver a key piece on time | No | [6 empty] | No
| 13 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | Working strategy for evidencing the outcomes and impacts of GLDC | Same as 2019 (This milestone has been completed in AR 2019, hence, to be dropped in POWB 2020) | Strategy | 1 | 1 | 1 | 1 | Medium | 4. Internal resources - risk that key staff, infrastructure or equipment not available at time needed | [8 empty] | The milestones highlighted in yellow have been confirmed to be completed in 2019 and shouldn’t be extended to 2020.
| 14 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | At least two GLDC new scaling projects supported to apply scaling toolkit | Identical to proposal | Project design documents | NA | NA | NA | NA | Medium | 6. External environment (political, economic, legal, market) - e.g. risk of non-delivery due to conflict, economic/ market changes | No | [6 empty] | No
| 15 | 1 | 1.4 | Conducive agricultural policy environment | FP1.04. Strong project design, execution, monitoring and evaluation systems and tools consistently applied in GLDC scaling projects, with demonstrable progress in enhanced adoption and impact | The working strategy for evidencing the outcomes and impacts of GLDC implemented | New | Working papers on impact assessment | 1 | 0 | 1 | 0 | Medium | 4. Internal resources - risk that key staff, infrastructure or equipment not available at time needed | No | [6 empty] | No